## Slide 1
✦
SOULFABLES · PHASE 0 DELIVERABLE
Architecture for the House
How Soulfables gets built so that it launches small, scales into the full
ecosystem, and never again fails to put a book in a customer’s hands.
PREPARED FOR
Apophia Kamwine
STATUS
Draft for review
SUPERSEDES
Base44 build
SCOPE
Web · Admin · Mobile
Notes: Phase 0 deliverable. The architecture document precedes any build, as the brief itself specifies.

## Slide 2
00
THE AUDIT
What we found
soulfables.co redirects to Base44. The live product is further along than the brief describes and that changes what this project is.
32
stories live
Across 27 shelves, four authors
5
products, not 1
Including a $45 bundle that must fan out
2
dead nav links
/wander and /residents return 404
Shelves are not categories.
They are emotional entry points with their own copy, a curated first read, and a Librarian’s note that deliberately sends readers elsewhere. The shelf labelled “Sleepless” lives at /shelf/anxiety label, URL and theme are already three different things.
The journey graph already exists. Each shelf states where readers arrive from and continue to that is the Intelligence Platform, already designed, just not yet computed.
Notes: Key reframe: this is a migration with live customers, existing content and indexed URLs not a greenfield build.

## Slide 3
✦
THE CONSEQUENCE
This is not a greenfield build.
It is a migration with live customers, existing content and indexed URLs —
and the brief is silent on all three.
Cutover is therefore scoped as work, not discovered during launch week. Existing buyers get entitlement rows so their books appear on day one; every legacy URL keeps its shape or gets a 301.
Notes: If the honest answer is "nothing worth carrying over", that is fine but it must be written down, not assumed.

## Slide 4
01
BEFORE BUILD
Five decisions only you can make
D1
How does Soulfables take money?
BLOCKS PHASE 2
D2
What carries over from Base44?
BLOCKS PHASE 3
D3
What is the budget ceiling?
SCOPES EVERYTHING
D4
May the AI read journal entries?
DESIGN CONSTRAINT
D5
Flutter, or share code with web?
PHASE 5
Notes: Two block the build. The other three get more expensive the later they are answered.

## Slide 5
D1
THE BLOCKING DECISION
Stripe will not work
Stripe does not support businesses registered in Rwanda. The brief names Stripe with “subject to availability” attached but this is a legal and tax decision before it is a technical one.
Merchant of record
Paddle · Lemon Squeezy
They become the legal seller absorbing both the entity problem and EU VAT on digital goods, which the brief never mentions. Higher fees, far less administration.
African payment infra
Flutterwave · Paystack
Supports RWF and MTN Mobile Money which matters if a meaningful share of readers are East African.
Stripe via foreign entity
US LLC · UK Ltd
Unlocks Stripe, but adds company formation, accounting and cross-border tax obligations.
Recommendation
A merchant of record for global card payments, with an African PSP added later if local sales justify it. The audience for a Rwandan author writing in English is likely split between diaspora and local readers and those two groups pay by different rails.
Notes: This must be resolved before Phase 2. Everything else in commerce is insulated from it by a provider adapter.

## Slide 6
02
THE STACK
Technical architecture
Web
Next.js 15 · React · TypeScript
Server rendering. Stories must be indexable.
Database
Supabase Postgres + RLS
Authorisation in the database, not the app.
Files
Supabase Storage three buckets
Public media, protected audio, paid files.
Payments
Provider-agnostic adapter
Pending D1. No vendor presupposed.
Mobile
Flutter · Riverpod · GoRouter
Phase 5. Dart types from the schema.
AI
Provider adapter · pgvector
Model choice stays swappable.
Notes: Two deviations from the brief, both toward less structure at the start: admin ships inside the web app, and workspace packages have no build step yet.

## Slide 7
✦
03 · DATABASE SCHEMA
Access to a file is never derived from an order, a session, a redirect, or anything the browser said only from a row in entitlements, written by a verified webhook.
This is the whole answer to the delivery problem.
•
Products have many files EPUB, PDF, future formats
•
Bundles fan out at grant time into one entitlement each
•
Refunds revoke; a partial index permits re-purchase
•
Webhook event ids are unique retries cannot double-grant
Notes: 12 migrations, ~50 tables. This is the sentence that matters most.

## Slide 8
05
DELIVERY FLOW
The chain that already failed once
UNTRUSTED the browser may lie about any of this
1
Product page
Price read from the database
2
Checkout begins
Amount computed server-side
3
Reader pays at provider
Card details never touch us
4
Browser returns
This page grants nothing
TRUSTED server-side, signature-verified
5
Webhook arrives
Signature verified, event logged
6
Order marked paid
Only this step may set paid_at
7
Entitlements granted
Bundles fan out to contents
8
Email sent and logged
Delivery answerable from the DB
The failure this prevents
If the webhook never arrives, the customer sees “we’re confirming your order” and an alert fires not a success screen with no book behind it. The failure mode of every bug in this chain is a customer who has to wait, never a stranger who gets the file.
Notes: Step 9: each download mints a short-lived signed URL after re-checking the entitlement, and logs the mint.

## Slide 9
06
SEVEN PHASES, RESEQUENCED ONCE
Development roadmap
Bookshop moves ahead of Library selling reliably is the problem Soulfables has today; the library is the problem it will have at scale.
P1
Foundation
3–4 wks
Repo, CI, schema, RLS, auth, design system, content operations
P2
Bookshop & delivery
4–5 wks
Checkout, webhook, entitlements, signed downloads, receipts
P3
Library & reader
4–5 wks
Migration with 301s, shelves, journey graph, reader, search
P4
Journal & Letter
2–3 wks
Private journal, prompts, moods, Letter archive, Wander
P5
Mobile
8–12 wks
Flutter iOS and Android, offline audio
P6
Intelligence
4–6 wks
Embeddings, recommendations, AI companion + safety layer
P7
Residents
4–6 wks
Community and membership, once the concept is decided
Launchable scope is P1–P3: 11–14 weeks for one senior developer.
Notes: Everything after P3 is a funded extension, not a prerequisite. Mobile is the largest discretionary cost in the project.

## Slide 10
07
PAYMENT TIED TO DEMONSTRATION
Milestones
M0
Architecture
This document approved; D1 and D2 answered; accounts created under Soulfables ownership
M1
Foundation
Soulfables publishes a story through admin with no developer involved
M2
Payment spike
A real test purchase produces a verified webhook, an entitlement, and a working download
M3
Bookshop
All five products purchasable; the bundle grants every contained product; refund revokes
M4
Security review
User A provably cannot reach User B’s orders, files or journal demonstrated live
M5
Library
All 32 stories migrated, every old URL 301s, reader works on phone and desktop
M6
Launch
DNS cut over, prior customers imported and emailed, monitoring live, rollback rehearsed
M7
Handover
A second developer runs the project locally from the README alone
Notes: Each milestone is a demonstrable capability, never a percentage complete.

## Slide 11
10
AUTHORISATION LIVES IN THE DATABASE
Security
Row Level Security is on for every table. A table with no policy is reachable only by the service role, which never ships to a browser or a phone.
Two deliberate exceptions
Staff cannot read journal entries. No policy grants it an admin sees that a reader has fourteen entries, never what any of them says.
No client role can write entitlements. Access is granted only by the service role, only after a verified webhook.
Paid files
Every EPUB and PDF lives in a private bucket with no read policy for anyone including the customer who owns the book.
Downloads are short-lived signed URLs minted server-side after the entitlement check, and every mint is logged.
Safety is a security concern here
A library about heartbreak, grief and healing, paired with an emotional AI companion, will meet readers in crisis. “Not a therapist” is necessary and nowhere near sufficient. The plan: a distress classifier on companion input, routing to region-appropriate crisis resources held in a table the House can correct without a deploy, no diagnostic language, and the journal consent rule enforced in the query rather than in a prompt.
Notes: Also: rate limiting, Zod validation at every boundary, append-only audit log, secrets in the platform store, quarterly access review.

## Slide 12
12
DEPLOYMENT
Cutover from Base44
1
Freeze content edits on Base44
2
Export stories to MDX; import with slugs preserved exactly
3
Import prior customers as paid orders with entitlements
4
Verify all 32 stories and the full checkout chain on staging
5
Publish the 301 map; test every legacy URL
6
Cut DNS in the lowest-traffic window, Base44 retained as rollback
7
Email prior customers that their library is ready
8
Watch error rates and webhook success for 48 hours
Backup and recovery
Daily Postgres backups with seven-day point-in-time recovery, plus a weekly off-platform export so recovery never depends on a single vendor account staying accessible. Target recovery point one hour, recovery time four hours.
Restores are rehearsed quarterly an untested backup is a belief, not a backup.
Notes: Four environments: local, per-PR preview, staging on an anonymised copy, production.

## Slide 13
13
BEFORE HIRING
Ownership is an account, not a clause
Create every one of these under a Soulfables address before a developer is engaged, then invite them in. Ownership you create is ownership you hold.
GitHub organisation
Member, write access
Supabase organisation
Developer role
Vercel team
Member
Payment account
Restricted API keys only
Domain registrar
No access required
Email sending
API key
Analytics & monitoring
Member
AI provider
Scoped key
One line to add to the brief
“No capability may be added that cannot be operated by Soulfables through
the admin dashboard or a documented runbook.”
That prevents developer lock-in more effectively than the ownership list, because it constrains the design rather than the paperwork.
Notes: Plus two contract additions: an explicit IP assignment clause, and no production secret existing solely on a developer machine.

## Slide 14
✦
NEXT
Answer D1 and D2.
Then the build begins.
How Soulfables takes money, and what carries over from Base44. Everything else in this document can proceed under a stated assumption those two cannot.
Every soul has a story. This is how it gets delivered.
Notes: The schema, RLS policies and design tokens already exist in the repository as evidence for this design not as a build head start.